## Sheet1
Risk ID | Risk Category | Hazard Description | Consequence | Likelihood | Risk Rating | Control Measures | Responsible Party | Consequence Score | Likelihood Score | Risk Score | Risk Level | Estimated Financial Impact (USD) | Calculation Method
R1 | Feedstock | Shortage of EFB or bagasse feedstock | Major | Possible | High | Diversified sourcing, inventory management | Supply Chain Manager | 5 | 3 | 15 | High | 30000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R2 | Road Conditions | Road damage during monsoon | Significant | Likely | Critical | Road maintenance partnerships | Logistics Manager | 4 | 4 | 16 | Critical | 32000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R3 | Seasonality | Seasonal feedstock variability | Moderate | Likely | High | Adaptive storage and inventory | Operations Manager | 3 | 4 | 12 | High | 24000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R4 | Shipping | Shipping delays due to port congestion | Major | Possible | High | Logistics planning and buffer time | Shipping Coordinator | 5 | 3 | 15 | High | 30000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R5 | Safety | Workplace accidents | Catastrophic | Possible | Critical | Safety training, PPE use | HSE Officer | 6 | 3 | 18 | Critical | 36000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R6 | Fuel Costs | Fluctuations in oil prices | Major | Likely | High | Long-term oil contracts | Finance Manager | 5 | 4 | 20 | Critical | 40000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R7 | Energy Costs | Rising electricity tariffs | Significant | Possible | Medium | Energy efficiency programs | Operations Manager | 4 | 3 | 12 | High | 24000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R8 | Trucking Costs | Increase in trucking rates | Major | Likely | High | Negotiated transport contracts | Logistics Manager | 5 | 4 | 20 | Critical | 40000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R9 | Operational | Process disruptions due to maintenance | Moderate | Possible | Medium | Preventive maintenance | Maintenance Supervisor | 3 | 3 | 9 | Medium | 18000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R10 | Supply Chain | Supplier failure to deliver on time | Significant | Possible | Medium | Supplier diversification | Supply Chain Coordinator | 4 | 3 | 12 | High | 24000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R11 | Environmental | Dust emissions from pellet processing | Moderate | Likely | High | Air filtration systems | Environmental Officer | 3 | 4 | 12 | High | 24000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R12 | Health & Safety | Fire in biomass storage | Catastrophic | Possible | Critical | Fire suppression systems | Safety Supervisor | 6 | 3 | 18 | Critical | 36000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R13 | Compliance | Non-compliance with RSPO standards | Major | Unlikely | Medium | Certification tracking | Compliance Officer | 5 | 2 | 10 | Medium | 20000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R14 | Financial | Exchange rate fluctuations | Significant | Likely | High | Currency hedging | Financial Analyst | 4 | 4 | 16 | Critical | 32000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R15 | Social & Community | Community protests | Moderate | Possible | Medium | Community engagement programs | Community Relations Officer | 3 | 3 | 9 | Medium | 18000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R16 | Reputational | Negative media coverage | Significant | Possible | Medium | Proactive communication strategy | Communications Manager | 4 | 3 | 12 | High | 24000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R17 | Technical | Software malfunction in WAMS | Moderate | Unlikely | Medium | System maintenance and updates | IT Systems Manager | 3 | 2 | 6 | Medium | 12000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R18 | Equipment Failure | Failure of key machinery | Major | Likely | High | Regular machine servicing | Plant Engineer | 5 | 4 | 20 | Critical | 40000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R19 | Data Security | Cyberattack on data systems | Catastrophic | Rare | Critical | Cybersecurity protocols | IT Security Officer | 6 | 1 | 6 | Medium | 12000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R20 | Legal | Breach of environmental regulations | Major | Unlikely | Medium | Legal compliance monitoring | Legal Advisor | 5 | 2 | 10 | Medium | 20000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R21 | Financial | Drop in pellet price per MT | Major | Possible | High | Long-term contracts, price hedging | Financial Manager | 5 | 3 | 15 | High | 30000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R22 | Operational | Increase in EFB feedstock cost | Major | Likely | High | Diversifying feedstock sources | Supply Chain Manager | 5 | 4 | 20 | Critical | 40000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R23 | Supply Chain | Labor strike affecting production | Significant | Unlikely | Medium | Labor agreements, flexible staffing | HR Manager | 4 | 2 | 8 | Medium | 16000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R24 | Logistics | Transport disruption due to road conditions | Significant | Possible | Medium | Alternative transport routes, backup carriers | Logistics Coordinator | 4 | 3 | 12 | High | 24000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25
R25 | Market | Decrease in pellet demand from key buyers | Major | Possible | High | Diversification of customer base, export readiness | Sales Manager | 5 | 3 | 15 | High | 30000 | Estimated Financial Impact = Base Cost ($50,000) * (Likelihood Score * Consequence Score) / 25